## Task Tracker Enhancement
Task Tracker
Task ID | Ref. Req ID | Task Description | Reources Allocated | Planned Start Date | Planned End Date | Planned Effort (hours) | Actual Start Date | Actual End Date | Actual Effort | Schedule Variance ( %) | Effort Variance ( %)
1 | 2.1.1 | Requirment Analysis | Amit/Rashid | 2014-10-22 | 2014-10-30 | 72 | 2014-10-25 | 2014-10-30 | 48 | 0 | -33.3333
2 | 2.1.2 | Data flow diagram | Minhaz | 2014-11-01 | 2014-11-03 | 24 | 2014-11-02 | 2014-11-03 | 16 | 0 | -33.3333
3 | 2.1.3 | Find out Main Business Process | Amit | 2014-11-01 | 2014-11-03 | 24 | 2014-11-01 | 2014-11-03 | 24 | 0 | 0
4 | 2.1.4 | DataBase Creation | Rashid | 2014-11-01 | 2014-11-05 | 40 | 2014-11-01 | 2014-11-05 | 40 | 0 | 0
5 | 2.1.5 | Solution Architecture Reformed | Rashid | 2014-11-06 | 2014-11-08 | 24 | 2014-11-07 | 2014-11-09 | 24 | 33.33 | 0
6 | 2.1.6 | Sourcesafe Configuration and Environment setup to Server | Mahfuz | 2014-11-09 | 2014-11-10 | 16 | 2014-11-09 | 2014-11-10 | 16 | 0 | 0
7 | 2.1.7 | Table Design for Setup Table | Minhaz | 2014-11-06 | 2014-11-10 | 40 | 2014-11-06 | 2014-11-10 | 40 | 0 | 0
8 | 2.1.8 | Review All DataBase Schema and Flow Diagram | Minhaz | 2014-11-11 | 2014-11-11 | 8 | 2014-11-11 | 2014-11-12 | 16 | 100 | 100
9 | 3.2.1 | Company Group Setup | Amit | 2014-11-12 | 2014-11-16 | 40 | 2014-11-12 | 2014-11-16 | 40 | 0 | 0
10 | 3.2.2 | Company Setup | Amit | 2014-11-17 | 2014-11-20 | 32 | 2014-11-18 | 2014-11-20 | 24 | 0 | -25
11 | 3.2.3 | Factory Setup | Amit | 2014-11-22 | 2014-11-27 | 48 | 2014-11-22 | 2014-11-27 | 48 | 0 | 0
12 | 3.2.4 | Branch Setup | Amit | 2014-11-29 | 2014-12-03 | 40 | 2014-11-29 | 2014-12-03 | 40 | 0 | 0
13 | 3.2.5 | Region Setup | Amit | 2014-12-03 | 2014-12-03 | 8 | 2014-12-03 | 2014-12-04 | 16 | 100 | 100
14 | 3.2.6 | Area Setup | Amit | 2014-12-04 | 2014-12-09 | 48 | 2014-12-05 | 2014-12-09 | 40 | 0 | -16.6667
15 | 3.2.7 | Division | Rashid | 2014-11-12 | 2014-11-16 | 40 | 2014-11-12 | 2014-11-16 | 40 | 0 | 0
16 | 3.2.8 | District | Rashid | 2014-11-17 | 2014-11-20 | 32 | 2014-11-17 | 2014-11-20 | 32 | 0 | 0
17 | 3.2.9 | Union | Rashid | 2014-11-21 | 2014-11-25 | 40 | 2014-11-21 | 2014-11-25 | 40 | 0 | 0
18 | 3.2.10 | Thana | Rashid | 2014-11-26 | 2014-11-30 | 40 | 2014-11-26 | 2014-11-30 | 40 | 0 | 0
19 | 3.3.1 | Employee Information Setup | Amit | 2014-12-10 | 2014-12-15 | 48 | 2014-12-10 | 2014-12-15 | 48 | 0 | 0
20 | 3.3.2 | Employee Transfer Tracking System | Amit | 2014-12-17 | 2014-12-21 | 40 | 2014-12-17 | 2014-12-21 | 40 | 0 | 0
21 | 3.4.1 | Product Type Setup | Minhaz | 2014-11-12 | 2014-11-17 | 48 | 2014-11-12 | 2014-11-17 | 48 | 0 | 0
22 | 3.4.2 | Product Master Setup | Minhaz | 2014-11-18 | 2014-11-25 | 64 | 2014-11-19 | 2014-11-26 | 64 | 12.5 | 0
23 | 3.4.3 | Product Detail setup | Minhaz | 2014-11-26 | 2014-12-02 | 56 | 2014-11-26 | 2014-12-02 | 56 | 0 | 0
24 | 3.4.4 | Package Specification | Minhaz | 2014-12-03 | 2014-12-08 | 48 | 2014-12-03 | 2014-12-08 | 48 | 0 | 0
25 | 3.4.5 | Inventory Head office | Amit | 2014-12-22 | 2014-12-27 | 48 | 2014-12-24 | 2014-12-27 | 32 | 0 | -33.3333
26 | 3.4.6 | Delivery Challan | Amit | 2014-12-28 | 2015-01-03 | 56 | 2014-12-28 | 2015-01-04 | 64 | 14.29 | 14.2857
27 | 3.4.7 | Inventory Stock Maintains | Minhaz | 2014-12-09 | 2014-12-14 | 48 | 2014-12-09 | 2014-12-14 | 48 | 0 | 0
28 | 3.4.8 | Received Challan Branch wise | Minhaz | 2014-12-15 | 2014-12-21 | 56 | 2014-12-15 | 2014-12-21 | 56 | 0 | 0
29 | 3.5.1 | New Leasing Creation | Rashid | 2014-12-01 | 2014-12-17 | 136 | 2014-12-01 | 2014-12-17 | 136 | 0 | 0
30 | 3.5.2 | Installment Collection | Rashid | 2014-12-18 | 2014-12-31 | 112 | 2014-12-18 | 2014-12-31 | 112 | 0 | 0
31 | 3.5.3 | Sales Return with depreciation | Rashid | 2015-01-01 | 2015-01-10 | 80 | 2015-01-01 | 2015-01-12 | 96 | 20 | 20
32 | 3.5.4 | Spare part sales | Rashid | 2015-01-11 | 2015-01-17 | 56 | 2015-01-12 | 2015-01-18 | 56 | 14.29 | 0
33 | 3.5.5 | Leasing Report | Rashid | 2015-01-18 | 2015-01-25 | 64 | 2015-01-18 | 2015-01-25 | 64 | 0 | 0
34 | 3.5.6 | Insatlment Report | Rashid | 2015-01-26 | 2015-02-05 | 88 | 2015-01-26 | 2015-02-07 | 104 | 18.18 | 18.1818
35 | 3.5.7 | Integration to Accounting for Opening Vaance | Mahfuz | 2014-11-12 | 2014-11-20 | 72 | 2014-11-12 | 2014-11-22 | 88 | 22.22 | 22.2222
36 | 3.6.1 | Chart of Creation Entry Form | Mahfuz | 2014-11-21 | 2014-11-26 | 48 | 2014-11-23 | 2014-11-26 | 32 | 0 | -33.3333
37 | 3.6.1.1 | Cash Payment Voucher | Mahfuz | 2014-11-27 | 2014-12-02 | 48 | 2014-11-27 | 2014-12-02 | 48 | 0 | 0
38 | 3.6.1.2 | Cash Received Voucher | Mahfuz | 2014-12-03 | 2014-12-07 | 40 | 2014-12-03 | 2014-12-07 | 40 | 0 | 0
39 | 3.6.1.3 | Bank Payment Voucher | Mahfuz | 2014-12-08 | 2014-12-15 | 64 | 2014-12-08 | 2014-12-17 | 80 | 25 | 25
40 | 3.6.1.4 | Journal Voucher | Mahfuz | 2014-12-17 | 2014-12-23 | 56 | 2014-12-18 | 2014-12-23 | 48 | 0 | -14.2857
41 | 3.6.1.5 | Bank Received Voucher | Mahfuz | 2014-12-24 | 2014-12-28 | 40 | 2014-12-24 | 2014-12-28 | 40 | 0 | 0
42 | 3.6.2 | Ledger | Mahfuz | 2014-12-29 | 2015-01-10 | 104 | 2014-12-29 | 2015-01-14 | 136 | 30.77 | 30.7692
43 | 3.6.3 | Trail balance, Balance Sheet | Mahfuz | 2015-01-11 | 2015-01-20 | 80 | 2015-01-15 | 2015-01-20 | 48 | 0 | -40
44 | 3.7.1 | Collection Efficiency | Amit | 2015-01-04 | 2015-01-08 | 40 | 2015-01-04 | 2015-01-09 | 48 | 20 | 20
45 | 3.7.2 | Recovery Rate | Amit | 2015-01-10 | 2015-01-17 | 64 | 2015-01-10 | 2015-01-18 | 72 | 12.5 | 12.5
46 | 3.7.3 | Advance And Partial Payment | Amit | 2015-01-18 | 2015-01-23 | 48 | 2015-01-19 | 2015-01-23 | 40 | 0 | -16.6667
47 | 3.7.4 | Outstanding ,Overduce Collection | Amit | 2015-01-24 | 2015-02-05 | 104 | 2015-01-24 | 2015-02-05 | 104 | 0 | 0

## Project Tracker
Project Name < Leasing And Integrated Accounting System >
Sl | Items | Planned Start Date | Planned End Date | Planed Effort ( Person Hrs) | Actual Start Date | Actual End Date | Actual Effort (Hrs) | SIZE (Object Points) | Schedule Varriance * | Effort Varriance | Total Defects | Defect Density | Remarks
1 | 1st bi-weekly status | 2014-10-22 | 2014-11-05 | 160 | 2014-10-25 | 2014-11-05 | 128 |  | 0 | -20 | 7 |  | Effort Variance is -20 which lesser then the range of the achieved goal (+/-10%) defined as per project plan. Need to Follow up and fill up the CAPA.
2 | 2nd bi-weekly status | 2014-11-06 | 2014-11-20 | 384 | 2014-11-06 | 2014-11-20 | 368 | 25 | 0 | -4.17 | 8 | 0.32 | Schedule Variance is 0 which is within the range of the achieved goal (+/-10%) and Effort Variance is -4.17 which is within the range of the achieved goal (+/-10%) defined as per project plan. But defect density is 0.32 which is greater than the achieved goal (0.1 – 0.3 defects / size). Need to Follow up and fill up the CAPA.
3 | 3rd bi-weekly status | 2014-11-21 | 2014-12-06 | 416 | 2014-11-22 | 2014-12-06 | 496 | 18 | 0 | 19.23 | 9 | 0.5 | Schedule Variance is 0 which is within the range of the achieved goal (+/-10%) and Effort Variance is 19.23 which is greater than the achieved goal (+/-10%) defined as per project plan. Also defect density is 0.5 which is greater than the achieved goal (0.1 – 0.3 defects / size). Need to Follow up and fill up the CAPA.
4 | 4th bi-weekly status | 2014-12-07 | 2014-12-21 | 444 | 2014-12-07 | 2014-12-21 | 512 | 38 | 0 | 15.32 | 14 | 0.37 | Schedule Variance is 0 which is within the range of the achieved goal (+/-10%) and Effort Variance is 15.32 which is greater than the achieved goal (+/-10%) defined as per project plan. Also defect density is 0.37 which is greater than the achieved goal (0.1 – 0.3 defects / size). Need to Follow up and fill up the CAPA.
5 | 5th bi-weekly status | 2014-12-22 | 2015-01-05 | 392 | 2014-12-22 | 2015-01-06 | 374 | 15 | 6.67 | -4.59 | 0 | 0 | Schedule Variance is 6.67 which is within the range of the achieved goal (+/-10%) and Effort Variance is -4.59 which is within the range of the achieved goal (+/-10%) defined as per project plan. And defect density is 0. So no need to Follow up and fill up the CAPA.
6 | 6th bi-weekly status | 2015-01-06 | 2015-01-20 | 366 | 2015-01-07 | 2015-01-20 | 336 | 36 | 0 | -8.2 | 0 | 0 | Schedule Variance is 0 which is within the range of the achieved goal (+/-10%) and Effort Variance is -8.2 which is within the range of the achieved goal (+/-10%) defined as per project plan. And defect density is 0. So no need to Follow up and fill up the CAPA.
7 | 7th bi-weekly status | 2015-01-21 | 2015-02-04 | 288 | 2015-01-21 | 2015-02-04 | 242 | 23 | 0 | -15.97 | 0 | 0 | Schedule Variance is 0 which is within the range of the achieved goal (+/-10%) and Effort Variance is -15.97 which is lesser than the achieved goal (+/-10%) defined as per project plan. And defect density is 0. So no need to Follow up and fill up the CAPA.
8 | 8th bi-weekly status | 2015-02-05 | 2015-02-19 | 24 | 2015-02-05 | 2015-02-19 | 24 | 12 | 0 | 0 | 0 | 0 | Schedule Variance is 0 which is within the range of the achieved goal (+/-10%) and Effort Variance is 0 which is within the range of the achieved goal (+/-10%) defined as per project plan. And defect density is 0. So no need to Follow up and fill up the CAPA.
Note : Schedule Variance and Effort Variance achieved goal is (+/-10%) defined as per project plan. Defect Density achieved goal is (0.1 – 0.38) as per project plan.
* Schedule verriance = (((actual end date - planned end date)/ (planned end date - planned start date)) + 1) * 100
* Defect Density = Total Defect/ object point

## Defect Data
Defect Data
SDLC Phases | Work Product | Reviewer | Planned Date | Actual Date | Review Effort (Hrs) | Total Defects found | Status | Rework effort (Person Hour)
Planning | Planning Review Check List | Tanvir,Sadat | 13/11/2014 | 14/11/2014 | 4 | 7 | Open | 5
Analysis | Requirment Spec. Review Checklist | Hasan,Sadat | 25/10/2014 | 25/10/2014 | 3 | 7 | Closed | 5
Design | Design Document Review | Tanvir | 2014-11-11 | 2014-11-11 | 3 | 1 | Open | 4
Coding | Coding Review Check List | Tanvir | 2014-11-25 | 2014-11-25 | 8 | 7 | Open | 7
Testing | [6 empty] | Open
|  |  |  | Total Defects | 18 | 22 |  | 21
Planning | Planning Review Check List | Tanvir,Sadat | 2014-08-12 | 2014-08-12 | 2 | 2 | Closed | 4
Analysis | Requirment Spec. Review Checklist | Hasan,Sadat | 30/11/2014 | 30/11/2014 | 2 | 2 | Closed | 3
Design | Design Document Review | Tanvir | 27/12/2014 | 27/12/2014 | 3 | 0 | Closed | 0
Coding | Coding Review Check List | Tanvir | 2015-01-10 | 2015-01-10 | 3 | 0 | Closed | 0
Testing (ST) | System Testing ST-01 | Hasan | 2015-01-12 | 12/01/205 | 1 | 0 | Closed | 0
Testing (UIT) | Test Specification and Review Check List | Hasan, Sadat | 2014-12-12 | 14/12/2014 | 4 | 12 | Closed | 5
|  |  |  | Total Defects | 15 | 16 |  | 12
Defect Data(Validation/Testing) of Leasig and Integrated Accounting System
Test Name | Work Product | Tester | Planned Date | Actual Date | Test Effort (Hrs) | Total Defects found | Status | Rework effort (Person Hour)
Unit Testing | Unit Test Cases
UT-A01 | ReqID-3.6.1, Chart of Accounts when update account code, Code does not Updated | Hasan | 15/12/2014 | 15/12/2014 | 1 | 1 | Close | 3
UT-A05 | ReqID-3.2.2, Accounts Positing Time execuation fail. | Hasan | 2015-01-01 | 2015-01-01 | 2 | 1 | Close | 4
Total |  |  |  |  | 3 | 2 |  | 7
UT-E2 | ReqID-3.3.2, Validation Problem | Hasan | 31/2/2014 | 31/12/2014 | 2 | 1 | Close | 4
UT-G3 | ReqID - 3.3.2 drop down list don’t loads with data | Hasan | 2014-02-11 | 2014-02-11 | 3 | 1 | Close | 2
Total |  |  |  |  | 5 | 2 |  | 6
UT-G5 | ReqID-3.2.5, On execution, show error for setup problem | Hasan | 2015-10-11 | 2015-11-11 | 1 | 1 | Close | 2
UT-G6 | ReqId-3.2.6 Data deleteon Problem delete is not work | Hasan | 2014-10-11 | 2014-11-10 | 4 | 1 | Close | 3
Total |  |  |  |  | 5 | 2 |  | 5
UT-R1 | ReqID- 3.7.1, Data deletion problem | Hasan | 2014-01-11 | 2014-02-11 | 1 | 1 | Close | 2
UT-G1 | ReqID:3.2.1 Update will occur and will be visible in grid | Hasan | 2014-11-12 | 2014-11-12 | 1 | 1 | Close | 2
UT-G2 | ReqID:3.2.2 Group name drop down should be active during update | Hasan | 13/11/2014 | 14/11/2014 | 1 | 1 | Close | 1
UT-I01 | ReqID:3.4.1 Update will occur and will be visible in grid | Sadat | 2014-11-17 | 2014-11-17 | 1 | 1 | Close | 1
UT-I02 | ReqID:3.4.2 Update will occur and will be visible in grid | Hasan | 2014-11-22 | 2014-11-22 | 8 | 1 | Open | 10
UT-I03 | ReqID:3.4.3 Data deleteion Problem and does not work | Sadat | 2015-07-01 | 2015-07-01 | 2 | 1 | Close | 3
Total |  |  |  |  | 14 | 6 |  | 19

## CAPA
Corrective and Preventive Action
Sl. NO | Month | Deviation of Goal/ Issues identified | Corrective Action Identified | Responsibility | Target Closure Date | Status | Preventive Action Identified | Responsibility | Target Closure Date | Status
1 | Oct-Nov | Effort Variance is -20 which lesser then the range of the achieved goal (+/-10%) defined as per project plan. | Requirements not collected properly because they were busy with their office work and did not provided proper time. | Ifteraz Hafiz | 2014-11-05 | Closed | Need to take more time from the client | Ifteraz Hafiz | 2014-11-05 | Closed
2 | Nov | Defect density is 0.32 which is greater than the achieved goal (0.1 – 0.3 defects / size). | The client had fail to give requirments documents clearly. Communication with client need to increase. | Ifteraz Hafiz | 2014-11-20 | Closed | Maintain always good communication with stakeholder. | Ifteraz Hafiz | 2014-11-20 | Closed
3 | Nov-Dec | Effort Variance is 19.23 which is greater than the achieved goal (+/-10%) defined as per project plan. Also defect density is 0.5 which is greater than the achieved goal (0.1 – 0.3 defects / size). | Requirement has been changed. New requirement has been added. Re-estimation required need to update project tracker. CM Procedure should be followed Effectively. Some master entry forms nedd to be re-developed. | Ifteraz Hafiz | 2014-12-06 | Closed | Requirment Analysis Should be done considering all stakeholder in initial stage. | Ifteraz Hafiz | 2014-12-06 | Closed
4 | Dec | Effort Variance is 15.32 which is greater than the achieved goal (+/-10%) defined as per project plan. Also defect density is 0.37 which is greater than the achieved goal (0.1 – 0.3 defects / size). | Because of the new requirement has been added for the Functional forms of the inventory module some rework required. | Ifteraz Hafiz | 2014-12-21 | Closed | good communication with stakeholder and requirment analysis should be done considering all stakeholder in initial stage. | Ifteraz Hafiz | 2014-12-21 | Closed

## Lesson Learn & Re-usable comp
LESSONS LEARNT
No | Description | Type |  |  | Summary
1 | Project Tracker | Best practice |  |  | Went wrong | 1
2 | Code Review | Best practice |  |  | Went right | 6
3 | Design Review | Went right |  |  | Best practice | 4
4 | Test Paln Review | Went right
5 | Project Status Report | Best practice
6 | Decision Analysis Resulation | Best practice
7 | Risk Tracker | Went wrong
8 | Matrics Measurment | Went right
9 | Requirements_Traceability Matrix | Went right
10 | Lesson Learn & Re-usable comp | Went right
11 | UT, System testing | Went right
Reusable code/Artifacts
S.No | Component that can be reused in the project | Project where the components was used | Version No | Effort (person days) to modify the component
1 | Project Plan | Planning | V1.0 | 60
2 | Test Plan | Planning | V1.0 | 36
3 | Design Documents | Design | V1.0 | 120
4 | SRS | Development | V2 | 90